## Equipment Schedule
item name | vendor country | project country | expected date | actual date | status | risk level
Blowout Preventer (BOP) Stack | China | Nigeria | 2026-04-10 | 2026-06-25 | at_risk | 5
Riser Tensioner System | Russia | Angola | 2026-05-01 | 2026-07-15 | at_risk | 5
Subsea Control Module (SCM) | China | Ghana | 2026-05-15 | 2026-07-01 | delayed | 4
Drilling Derrick Structure | Russia | Nigeria | 2026-05-20 | 2026-07-20 | delayed | 4
High-Pressure Mud Pump Assembly | China | Angola | 2026-06-01 | 2026-07-28 | at_risk | 5
Mooring Chain & Anchor Set | North Korea | Ghana | 2026-04-25 | 2026-08-10 | at_risk | 5
Topside Process Module (Mod-1) | Philippines | Nigeria | 2026-06-10 | 2026-06-28 | delayed | 3
Marine Diesel Generator Set | Vietnam | Angola | 2026-06-20 | 2026-07-08 | delayed | 3
Crane Pedestal & Boom Assembly | India | Ghana | 2026-07-01 | 2026-07-14 | delayed | 3
Heating, Ventilation & AC Unit | Mexico | Nigeria | 2026-05-25 | 2026-06-07 | at_risk | 3
Emergency Shutdown Valve (ESD) | South Korea | Angola | 2026-07-05 | 2026-07-18 | delayed | 3
Corrosion Inhibitor Chemical Skid | Germany | Ghana | 2026-05-10 | 2026-05-12 | on_track | 1
Life Raft & Safety Equipment Set | Norway | Nigeria | 2026-06-01 | 2026-06-02 | on_track | 1
Navigation & Communication Suite | Japan | Angola | 2026-05-28 | 2026-05-29 | on_track | 2
Subsea Pipeline Insulation Joints | South Korea | Ghana | 2026-06-15 | 2026-06-17 | on_track | 2
Helideck Structure & Lighting | Netherlands | Nigeria | 2026-07-10 | 2026-07-11 | on_track | 1
Umbilical Cable (Chemical & Elec.) | Germany | Angola | 2026-07-20 | 2026-07-21 | on_track | 1
Fire & Gas Detection System | USA | Ghana | 2026-06-05 | 2026-06-06 | on_track | 1