## Equipment Schedule
item name | vendor country | project country | expected date | actual date | status | risk level
Gas Turbine Compressor Train | China | Indonesia | 2026-04-20 | 2026-06-30 | at_risk | 5
Amine Absorber Column (V-101) | China | Malaysia | 2026-05-05 | 2026-07-10 | delayed | 4
High-Voltage Transformer (132kV) | Russia | Vietnam | 2026-05-25 | 2026-07-20 | at_risk | 5
Slug Catcher Vessel Assembly | China | Thailand | 2026-06-01 | 2026-07-25 | delayed | 4
Cryogenic Cold Box Module | China | Indonesia | 2026-06-10 | 2026-08-01 | at_risk | 5
Glycol Regeneration Package | India | Malaysia | 2026-06-15 | 2026-06-28 | delayed | 3
Flare Knockout Drum (V-201) | Philippines | Vietnam | 2026-07-01 | 2026-07-13 | delayed | 3
Air Cooled Heat Exchanger Bank | Vietnam | Thailand | 2026-06-25 | 2026-07-08 | delayed | 3
Instrument Air Compressor Package | South Korea | Indonesia | 2026-05-20 | 2026-06-02 | at_risk | 3
Boiler Feed Water Pump Skid | Japan | Malaysia | 2026-07-10 | 2026-07-22 | delayed | 3
DCS Control Room Enclosure | India | Vietnam | 2026-05-30 | 2026-06-10 | at_risk | 3
Pipe Rack Structural Steel (A) | South Korea | Thailand | 2026-05-15 | 2026-05-17 | on_track | 2
Safety Shower & Eyewash Stations | Germany | Indonesia | 2026-05-20 | 2026-05-21 | on_track | 1
Custody Transfer Flow Meter | Switzerland | Malaysia | 2026-06-01 | 2026-06-02 | on_track | 1
Electric Heat Tracing System | Germany | Vietnam | 2026-06-10 | 2026-06-11 | on_track | 1
Gas Chromatograph Analyzer | USA | Thailand | 2026-06-20 | 2026-06-21 | on_track | 1
Storage Tank (Fixed Roof, T-301) | Taiwan | Indonesia | 2026-07-01 | 2026-07-03 | on_track | 2
Electrical Area Classification Map | Japan | Malaysia | 2026-07-15 | 2026-07-15 | on_track | 1
Process Interconnecting Pipework | South Korea | Vietnam | 2026-07-20 | 2026-07-22 | on_track | 2